Relationship Bridge (RB)

V1 Launch Plan

Scope, phased milestones, team, source acquisition, beta, go/no-go gates

Version 1.0  •  May 2026

# Abstract

This plan takes Relationship Bridge from its current state to V1 General Availability in 30 weeks. V1 ships a vertical-focused product (US restaurant / hospitality) covering the four feature areas at intentionally narrow depth: a working Daily Briefing, a four-verb subset of the Action Recommendation Policy, a lite Company Profile, and DRR v1 powering them. Network Gap detection ships as a preview, not a primary surface.

Five milestones — kickoff (M0), pipeline alpha (M1), DRR + briefing alpha (M2), closed beta (M3), beta exit (M4), GA (M5) — gate the plan. Each gate has a written go/no-go criterion. The biggest non-engineering risk is source acquisition, which starts at week zero and runs in parallel to all engineering.

# 1. V1 Scope

## 1.1 In scope

- Vertical: US restaurant / hospitality industry (QSR, fast-casual, multi-unit, franchise).

- Ingestion: mainstream business news + 6–8 trade publications + LinkedIn ecosystem signal + 1–2 podcast sources.

- Signal pipeline: classification, the 7 confidence tags, strategic interpretation with citation guardrails, and second-order implications.

- Relationship graph: per-user with the schema in §7 of the architecture spec; DRR v1 with default parameters.

- Action engine: 4 of 8 verbs at launch — congratulate, reconnect, monitor, no_action_recommended. Plus the restraint layer.

- Daily Briefing surface (web).

- Company Profile — lite version (momentum, vulnerability, relationships panel, signal timeline; no peer set or AI posture).

- Evaluation framework: offline metrics live; closed-beta A/B framework operational.

- Settings: focus areas, cooldown windows, declined-targets list, basic feedback.

- Mobile: read-only access to briefing (responsive web; native app deferred).

## 1.2 Out of scope for V1

- Vertical expansion beyond restaurant/hospitality.

- Verbs: request_meeting, investigate, share_article, strengthen (V2).

- Network Gap detection as a primary surface (preview-only in beta; full in V2).

- Multi-region operations.

- Webhooks / external API.

- Native mobile apps.

- Conference / podcast deep ingestion automation (manual ingestion at launch).

- AI Posture classification (V2).

- Peer set + comparative scoring (V2).

## 1.3 Quality bar for V1

- Median briefing latency to user view: ≤ 9 AM local on weekdays.

- Hallucination rate (failed citation guardrail): < 0.5% of strategic interpretations served.

- Top-of-briefing precision@5 (beta cohort, user-confirmed): ≥ 0.50.

- Restraint correctness ≥ 0.80 in closed beta.

- Per-user LLM cost within budget (defined at M2 gate).

# 2. Vertical Strategy

Restaurants / hospitality is the launch vertical. The direction document's examples concentrate here, the trade-press landscape is well-defined, and the persona (multi-unit operator, vendor exec, partnership leader) is sharply identifiable.

## 2.1 Why vertical-first

- Sharp persona means sharp source list, sharp scoring, and sharp recommendations.

- Source licensing economics are tractable for a focused vertical.

- Evaluation set can be built by hand at vertical scope; not at horizontal scope.

- Quality bar is higher because users can tell when the system is wrong.

- Wedge-to-expand is well-trodden: a credible product in one vertical opens adjacent verticals more cheaply than a horizontal launch.

## 2.2 Target sub-segments at launch

- Multi-unit QSR operators (HQ leadership and tech buyers).

- Enterprise POS, payments, and labor-tech vendors.

- Franchise leadership at the brand and franchisee level.

- Hospitality technology operators and investors.

- Strategic advisors and operators-turned-investors in the space.

## 2.3 Adjacent verticals for V2

In order of seriality based on persona-similarity and ecosystem overlap:

- Convenience retail / fuel.

- Specialty retail (grocery, beauty, home).

- Healthcare staffing / multi-site healthcare ops.

- Real estate / multi-site services.

# 3. Timeline & Milestones

## 3.1 Phase summary

| Milestone | Week | Definition |
| --- | --- | --- |
| M0 — Kickoff | 0 | Team in place. Source registry seeded. Working dataset of fixture signals. |
| M1 — Pipeline alpha | 6 | Ingestion + normalization + signal classification running on 3+ trade sources. Citation guardrail enforced. |
| M2 — DRR + briefing alpha | 12 | DRR v1 computed for a synthetic user graph. Daily Briefing renders 3–7 items with restraint behavior. |
| M3 — Closed beta | 18 | 10–20 users; full feature set as defined in §1.1. Eval framework live; weekly tuning. |
| M4 — Beta exit / GA gate | 26 | Quality bar met across go/no-go gates (§6). Source contracts in place. |
| M5 — V1 GA | 30 | General availability; controlled ramp from 20 → 100 users. |

# 4. Team Plan

Lean V1 team. Engineering-heavy with a designated data-ops/legal lead because source acquisition is on the critical path.

## 4.1 Roles & ownership

| Role | Count | Owns |
| --- | --- | --- |
| Engineering lead / architect | 1 | End-to-end pipeline, layer contracts, on-call rotation. |
| Backend engineer (pipeline) | 2 | Ingestion, normalization, signal pipeline, storage. |
| Backend engineer (graph + scoring) | 1 | Relationship graph, DRR, correlation, scoring. |
| ML engineer | 1 | LLM tier strategy, prompts, evals, citation guardrail. |
| Frontend engineer | 1 | Daily Briefing, Action Queue, Company Profile, Settings. |
| Designer (part-time) | 0.5 | Briefing UX, restraint UI, profile layouts. |
| Product manager | 1 | Roadmap, beta program, eval-set curation. |
| Data / source operations lead | 1 | Source registry, publisher relationships, licensing. |
| Customer success / beta manager | 0.5 | Beta onboarding, weekly feedback synthesis. |
| Legal counsel (contract) | 0.25 | Source agreements, ToS, privacy review. |

Total V1 team: ~7 FTE engineering + 1 PM + 1 data-ops + part-time design / CS / legal.

## 4.2 Decision rights

- Product scope changes — PM with input from engineering lead.

- Quality gates — PM + engineering lead jointly; either can block GA.

- Source contracts — data-ops lead with legal sign-off.

- Algorithm changes — ML engineer with eval-set evidence; engineering lead final approval.

# 5. Source Acquisition Strategy

Source acquisition is the #1 non-engineering risk and runs in parallel from week zero. Licensed trade content is hard to get and slow to negotiate; the plan must accommodate that.

## 5.1 Source tiers

| Tier | Examples | Acquisition path | Lead time |
| --- | --- | --- | --- |
| RSS / open trade | QSR Magazine, Restaurant Business | Standard RSS + terms review. | 2 weeks |
| Licensed trade | NRN, Hospitality Technology, premium franchise pubs | Direct license; publisher contract. | 8–14 weeks |
| Newsletter (operator) | Specific operator-written Substacks, paid newsletters | Subscriber-class license + author engagement. | 4–8 weeks |
| Earnings / transcripts | Vendor API (AlphaSense / Seeking Alpha) | Vendor contract. | 4–6 weeks |
| LinkedIn / social | Authorized API + accepted ToS scraping. | Vendor or in-house pipeline. | 4 weeks |
| Podcasts | RSS + transcription pipeline. | Standard. | 2 weeks |
| Conference content | Manual ingestion at launch; vendor pipeline V2. | Editorial team. | Ongoing |

## 5.2 Critical-path source list (must-have by M2)

- QSR Magazine — open / RSS.

- NRN (Nation's Restaurant News) — licensed.

- Restaurant Business — open.

- Hospitality Technology — licensed.

- At least one franchise-focused trade publication — open or licensed.

- AlphaSense or equivalent transcript vendor — contracted.

- LinkedIn ecosystem pipeline — operational.

## 5.3 Risk mitigations

- Start negotiations week zero — do not wait for engineering readiness.

- Maintain two viable paths per licensed source (e.g., direct contract or scraping under fair-use review).

- Establish editorial fallback: if a critical source is delayed, manual ingestion bridges to closed-beta start.

- Publisher partner program: offer revenue share or co-marketing where useful.

- Avoid hard dependencies on any single source — pipeline tolerates outages.

# 6. Go/No-Go Gates

Each milestone has a written criterion that must be true to advance. Any criterion failing blocks the milestone.

## 6.1 M1 gate (pipeline alpha) — week 6

- Ingestion working for ≥ 3 trade sources end-to-end.

- Signal classifier accuracy ≥ 0.90 on labeled fixture set.

- Citation guardrail catches ≥ 0.99 of unanchored interpretations on adversarial set.

- Per-signal Tier-1 LLM cost within projected envelope.

- Source registry populated; licensing decisions documented for all live sources.

## 6.2 M2 gate (DRR + briefing alpha) — week 12

- DRR computed for synthetic user graph; offline precision@10 on hand-labeled set ≥ 0.45.

- Briefing renders 3–7 items reliably; quiet-day output works.

- All four V1 verbs (+ restraint) producing recommendations with audit trails.

- End-to-end signal latency p95 ≤ 30 minutes.

- Eval framework operational (regression suite, drift monitors, dashboard).

## 6.3 M3 gate (closed beta start) — week 18

- 10–20 beta users contracted and onboarded.

- All in-scope features (§1.1) shipped behind feature flags.

- Critical-path source list complete (or editorial bridge in place).

- Privacy review complete; tenant isolation verified by internal audit.

- On-call rotation established; SLO dashboards live.

## 6.4 M4 gate (beta exit / GA approval) — week 26

- Top-of-briefing precision@5 ≥ 0.50 across the beta cohort (rolling 30 days).

- Restraint correctness ≥ 0.80.

- Hallucination rate (citation-guardrail failures reaching users) < 0.5%.

- Beta NPS or qualitative sentiment positive; user-reported false-positive rate ≤ 15%.

- No P0 incidents in the final 4 weeks of beta.

- All source contracts signed or with documented mitigation paths.

- Cost per active user within target envelope.

If a gate fails: Hold the milestone; identify the root cause; either tune-and-retry or descope. Schedule slip is preferred to shipping a missed gate.

# 7. Beta Program

## 7.1 Profile of beta users

- 10–20 users at M3, scaling to 25–30 by M4.

- Composition: 50% multi-unit operators or operator-adjacent execs; 30% vendors; 20% advisors/investors.

- All have a relationship graph of 200+ contacts they can import.

- All have stated focus areas inside the launch vertical.

- Mix of large-graph (1000+) and mid-graph (200–500) users to stress the system.

## 7.2 Operating model

- Weekly user check-ins with PM/CS during beta.

- Bi-weekly tuning windows: weight changes reviewed against eval framework.

- Per-user feedback channel; structured weekly synthesis.

- Office-hours support during beta (no on-call SLA externally communicated).

- Each user assigned a 'beta partner' inside the team for direct feedback.

## 7.3 Beta exit criteria

- Meet all M4 gate criteria.

- ≥ 70% of beta users actively using the product weekly in the final 4 weeks.

- ≥ 50% of beta users would recommend to a peer (structured exit survey).

# 8. Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Source licensing slips past M2 | High | High | Start week 0; maintain two paths per source; editorial fallback for the 1–2 most critical. |
| LLM costs exceed envelope | Medium | High | Tier-3 cap with Tier-2 fallback (architecture §12); aggressive caching; conservative defaults; reset cap at M2 with real numbers. |
| Hallucination rate above target | Medium | High | Citation guardrail (§5.3 arch); adversarial canary set; refuse-to-interpret behavior. |
| DRR rankings feel arbitrary to users | Medium | High | Eval framework live by M2; weight changes only via offline-pass gate; explainability in UI from M3. |
| Beta users churn from low precision in early weeks | Medium | Medium | Conservative restraint defaults; quiet-day output; weekly tuning; user-facing 'why am I seeing this?' |
| A privacy / data-handling incident | Low | High | Tenant isolation verified at M3; legal review of all sources before they go live; structured incident response. |
| A key source publisher refuses or removes access | Medium | Medium | No hard single-source dependencies in pipeline; degrade gracefully; editorial bridge during recovery. |
| Engineering attrition mid-build | Low | High | Cross-staffed layers; documented contracts; rotating on-call from M2. |
| Feature scope creep | Medium | Medium | PM owns scope; out-of-scope V1 list is final; V2 backlog is the relief valve. |

# 9. Post-V1 Roadmap Preview

V1 is the wedge. V2 and V3 expand both feature surface and vertical reach.

## 9.1 V2 — Months 8–14 post-GA

- Remaining 4 verbs: request_meeting, investigate, share_article, strengthen.

- Network Gap detection promoted to a primary surface.

- Company Profile full version (peer set, AI posture, comparative scoring).

- Power-shift detection live.

- Conference + podcast automated ingestion.

- First adjacent vertical: convenience retail / fuel.

## 9.2 V3 — Months 14–24 post-GA

- Multi-vertical rollout (specialty retail, healthcare staffing, multi-site services).

- Webhooks + external API.

- Native mobile app.

- Cross-tenant anonymized learning (consent-gated) for global default weights.

- Advanced second-order interpretation and gap-vector synthesis.

# 10. V1 Success Metrics

Read these alongside the architecture's §13 anti-metrics — none of those metrics is a V1 target.

## 10.1 Leading

- Briefing weekly active users (open + act).

- Top-of-briefing precision@5.

- Restraint correctness (no-action agreement rate).

- Per-recommendation accept / dismiss / snooze distribution.

- Citation guardrail pass rate.

## 10.2 Lagging

- User-reported opportunities attributable to RB triggers.

- Relationship reactivation rate (cold → warm).

- Beta-cohort 90-day retention.

- NPS or equivalent qualitative sentiment trend.

## 10.3 Non-goals

- Total signals ingested.

- Briefing items shown per user.

- Outreach messages sent.

- Session length / DAU as a primary metric.

# 11. Budget & Cost Envelope

Funding the 30-week plan. Headcount and infrastructure carry the cost; LLM spend is the only line item with operational variance.

## 11.1 Headcount cost (30 weeks)

- 7 FTE engineering + 1 PM + 1 data-ops, fully loaded, at industry-typical rates for a Series-A team. Designer, CS, and legal are part-time / contract.

- Headcount is the dominant cost line and is fixed once the team is hired.

- A re-baseline review is required at M2 (week 12) if the engineering team has not closed two of the four backend roles.

## 11.2 Infrastructure & LLM

- Storage, compute, queueing, observability: budgeted at a Tier-1 cloud provider. Single-region at GA.

- LLM spend: tiered per architecture §12 (Tier-3 cap with Tier-2 fallback). Per-user envelope is set at the M2 gate using real numbers from the synthetic-graph run. Until then, treat as the largest single risk to unit economics.

- Aggressive caching of normalized signal interpretations; cache hits should bear >60% of beta-day load by M3.

- Source licensing cost: tracked as a separate line item (§5); budget for two licensed trade publications and one transcript vendor.

## 11.3 Unit-economics target at GA

- Per-active-user variable cost (LLM + storage + per-source amortization) must come in at less than 25% of per-user revenue at the stated GA price band (§13).

- If unit cost overruns the envelope at M4, GA is held until either tiering tightens or the price band moves. Holding the gate is preferred to launching with broken margins.

# 12. Privacy, Security & Data Governance

A relationship-graph product handles personal contact data, employment history, and signal-derived inferences about people. Privacy posture is a launch-blocking concern, not a polish item.

## 12.1 Tenant isolation

- Per-user relationship graphs are strictly isolated; no cross-tenant signal flow at V1. Anonymized cross-tenant learning is deferred to V3 and is consent-gated.

- Internal audit at M3 must verify that no query path returns rows owned by another tenant.

- Backups and snapshots inherit the same isolation rules. No shared-key store across tenants.

## 12.2 Contact-data handling

- Imported contact lists (LinkedIn export, Google Takeout, CSV) are stored encrypted at rest. Field-level encryption for email and phone is required.

- Contact deletion: a user can purge a single contact or their whole graph within 24 hours of request; deletion includes derived briefs and DRR history.

- No third-party enrichment without explicit user opt-in. Default posture is do-not-enrich.

## 12.3 Source data & licensing compliance

- Every source has a recorded licensing decision and a kill-switch flag. A publisher can be removed from production in a single deploy.

- Outputs include source attribution end-to-end; the citation guardrail makes attribution-less interpretation impossible by construction.

- LinkedIn-derived data follows LinkedIn ToS; scraped pipelines, if used, are gated by legal review and have a documented fallback.

## 12.4 Incident response

- On-call rotation live from M2. P0 (data exposure or cross-tenant leakage) requires a written postmortem within 5 business days.

- Customer disclosure within 72 hours of confirmed exposure of their data; faster if their data appears in another tenant’s context.

# 13. Pricing & Commercial Model

V1 prices the wedge, not the platform. Decided in coordination with the unit-economics envelope in §11.3.

## 13.1 Beta commercial terms

- Closed beta is free. Beta users sign a one-page agreement covering feedback obligations, data-use boundaries, and a courtesy clause on confidentiality of unreleased features.

- Beta users are offered preferred GA pricing for 12 months (target: 50% discount off list).

## 13.2 GA pricing posture

- Per-seat monthly subscription. Single tier at GA. Annual prepay preferred; month-to-month available at a premium.

- Target price band: positioned above generic CRM add-ons (Hubspot, Affinity); below executive intelligence services (Tegus, Wonder). Final band is set by the M4 commercial review with two anchor reference accounts.

- Graph-size cap on the base tier; over-cap pricing is metered. Caps are public.

- No usage-based LLM billing exposed to the customer. Cost discipline is the operator’s problem, not the user’s.

## 13.3 Sales motion

- Founder-led / PM-led at GA. No sales hire in V1.

- 14-day evaluation with full functionality; no credit card to start.

- Channel partners deferred to V2. Direct-only at V1 to keep the feedback loop tight.

# 14. Founder Dogfooding

The founder’s own RB instance is the canonical eval ground. Treat it as production from week zero.

- The file-based RB instance (this repository) is V0. Its baseline graph, loop ledger, cards, and briefs are real-world ground truth for DRR, restraint, and recommendation behavior.

- The deterministic scripts in system/scripts/ (daily_brief, validate_baseline, gap_detection, loop_parser, network_gap, drr_score) are the reference implementation behaviors V1 must replicate or improve. Treat the script outputs as the V0 eval baseline.

- The founder operates the V0 system daily and reports observed misranks, missed loops, false-positive recommendations, and restraint failures into the V1 eval set.

- Every V1 behavior change must be sanity-checked against the founder’s graph before any beta user sees it.

- At M3, the founder’s graph is migrated onto the V1 platform and run side-by-side with V0 for at least four weeks. A divergence above an agreed threshold blocks beta exit.

# Appendix A — Week-by-Week Working Backlog (top-line)

| Weeks | Focus | Key deliverables |
| --- | --- | --- |
| 0–2 | Foundation | Team in place; source registry seeded; eval set v0; legal kickoff with publishers. |
| 2–6 | Ingestion + normalization | RSS connectors; entity resolution; first three trade sources end-to-end. |
| 4–10 | Signal pipeline | Classification, tagging, interpretation, second-order, citation guardrail. |
| 6–14 | Graph + DRR v1 | Schema, ER into graph, DRR computation, streaming updates. |
| 10–18 | Correlation + action engine | Rule engine, 4 verbs, restraint layer, audit log. |
| 12–22 | Briefing + profile UI | Daily Briefing, lite Company Profile, settings, feedback inputs. |
| 4–22 | Eval + monitoring | Fixture set, offline metrics, drift monitors, dashboards. |
| 18–26 | Closed beta | Onboarding, weekly tuning, qualitative synthesis. |
| 24–30 | Hardening + GA | SLOs, on-call, runbooks, GA ramp 20 → 100. |

# Appendix B — Beta-Cohort Recruiting Profile

| Attribute | Target |
| --- | --- |
| Graph size | 200–2,000 contacts importable |
| Role | Multi-unit operator, vendor exec, advisor, investor in the vertical |
| Engagement | Willing to give 30 min/week to feedback |
| Tolerance | Tolerant of a beta-quality product with explicit restraint |
| Geography | US-based |
| Diversity | Mix of operators, vendors, and investors; mix of graph sizes; mix of focus breadth |

# Appendix C — Source Registry Starter List

Concrete list of sources to begin acquisition against in week zero. Status updates live in the source registry, not here. Treat this appendix as the seed, not the inventory.

- Open / RSS: QSR Magazine, Restaurant Business, Modern Restaurant Management, Restaurant Dive, FastCasual.com, Franchise Times (open feeds where available).

- Licensed trade (target by M2): Nation’s Restaurant News (NRN), Hospitality Technology, Restaurant Finance Monitor, Franchise Update.

- Operator newsletters (paid subscriber-class licenses): a curated set of 4–6 operator-written Substacks identified by data-ops at week 0.

- Earnings / transcripts: AlphaSense or Seeking Alpha vendor contract. Targets: publicly traded operators and POS / payments vendors active in the vertical.

- LinkedIn: authorized API where available; in-house ToS-compliant scrape path as a redundant route.

- Podcasts: RSS + Whisper-class transcription. Target hosts: 5–7 podcasts indexed by data-ops in week 0.

- Conferences: manual editorial ingestion at V1 (NRA Show, FSTEC, Restaurants Rise, Hospitality Industry Technology Exposition).

# Appendix D — Evaluation Set Construction

A vertical-scope eval set is the single tool that lets a small team make principled trade-offs. Without it, weight changes turn into vibes.

## D.1 Composition

- 300–500 hand-labeled signal items from the launch vertical, sampled across all source tiers in §5.

- Each item carries: ground-truth classification, expected confidence tag, gold strategic interpretation (or “refuse”), and the cited evidence span.

- An adversarial subset (~60 items): unanchored claims, near-duplicates from different sources, ambiguous corporate-action events.

- A graph subset (40–60 synthetic users with imported real-shape graphs) for DRR precision⁀k offline measurement.

## D.2 Construction process

- Week 0–2: PM + ML engineer label v0 (target ~100 items). Inter-rater check on a 20-item sample.

- Week 2–6: add the trade-source items as ingestion goes live; build the adversarial subset deliberately by mining false positives.

- Week 6–12: graph subset built from a mixture of the founder’s graph (§14) and 3–5 synthetic graphs hand-constructed from public org data in the vertical.

- From M3 forward: beta-user feedback events feed back into the eval set with an explicit re-label step (no silent ground-truth drift).

## D.3 Use rules

- No weight change ships without an offline-pass result from the regression suite.

- The eval set is versioned; the version that gated each shipped model change is recorded in the change log.

- Drift monitors compare live distributions to the eval set; if drift exceeds the threshold for two consecutive weeks, the set is refreshed before further weight changes.