## Blue Sheet
SUBWAY — BLUE SHEET ¦ INTERNAL WORKING DRAFT
Field | Current read | Confidence / status | Evidence / next validation
Single sales objective | Win applicable NA connected restaurant RFP scope: kiosk/KDS, installation and managed services, and/or DMB through a compliant, affordable September 22 response. | Working objective | Subway RFP Enclosures 1–3, 5
Customer stated objective | Select preferred vendor(s) whose solutions meet or exceed documented requirements for scope(s) bid. | Customer RFP, high | Rules of Engagement §1, §9
Opportunity stage | Active competitive RFP; final submission due September 22, 2026. | Confirmed, high | Kiosk/KDS RFP Instructions; Enclosure 5
Planned scale | Up to 5,000 U.S. restaurants; price using three kiosks per store. 2026 phasing conflicts: 25 vs 200; about 4,800 in 2027. | RFP planning assumption, high | Market Coverage r14 vs Instructions r17; clarify formally
Current position | Existing reported Genius KDS relationship and stated SPOS-to-KDS API integration; deployment and outcome data unverified. | Reported, medium | Draft Integration & Environment r15; prior account brief
Primary red flags | Blank pricing; incomplete integration, hardware and services responses; kiosk-to-SPOS integration not currently built; Worldpay/Genius alignment incomplete. | Draft tracker and call evidence | Completion tabs, Integration & Environment; JPR 07:39/10:00
Competition | Current bidders and incumbent positions unknown. First call mentioned possible NCR activity; PAR history does not prove current bid position. | Unknown / reported | JPR 07:39; PAR 10-Ks; verify through formal process
Relationship change | First call reports two unanswered outreach attempts to a new Subway technology leader formerly at RBI and the departure of another Subway contact. Names/roles unclear. | Reported, medium | JPR 07:39; confirm through internal account records
PAR chronology | First call recalls a further PAR account loss about five or six years ago, potentially distinct from the reported 2000–01 hardware loss. | Reported, low | JPR 07:39; reconcile contracts and filings
Kiosk decision | Bid team discussed pricing and choosing current versus next-generation kiosk offering; Nick reportedly attends daily RFP calls. | Reported, medium | JPR 07:39; technical/commercial decision needed
Commercial hypothesis | Win requires a per-store cost bridge, clear payer, installation model, 120-day price validity, and approved capacity. | Hypothesis | 2024 FDD, QSR 50 2026, RFP Enclosure 5
Team posture | Nick leads bid; Worldpay relationship manager Stacey should align internally; final global account manager and commercial signer unconfirmed. | Reported / open | Rules of Engagement draft roster; JPR 07:39/10:00
Go / No-Go | Pending technical, pricing, capacity, and legal submission gates. | Working decision | Review before September 18 internal target

## Qualification
QUALIFICATION AND POSITION
Test | Read | Y / N / U | Required action
Budget / payer | RFP requests pricing but corporate/franchisee funding and cost ceiling unverified. | U | Confirm payer and model store cohorts.
Access | Procurement and technical event contacts named; customer sponsor and buying influences unverified. Worldpay relationship needs reconciliation. | U | Align internally; use formal RFP channel.
Buying process | RFP rules, Q&A and response dates documented; post-award decision path conditional. | U | Confirm evaluation and award process when permitted.
Technical fit | SPOS-to-KDS API is reported; kiosk-to-SPOS integration missing; payment/MDM/network/ADA responses incomplete. | U | Prove compatibility requirement by requirement.
Rollout capacity | Up to 5,000-store plan; 2026 phase discrepancy; maximum capacity response blank. | U | Quantify installed stores, staffing, OEM and partner constraints.
Coach | No customer coach verified. | U | Avoid assigning a coach from relationship history alone.

## Buying Influences
KNOWN CONTACTS — ROLE RATINGS UNVERIFIED
Person / team | Known role | Influence rating | Status / evidence
Brian Bancroft | Primary Subway RFP contact — Procurement | Unknown | Rules of Engagement §3; no buying role assigned.
Amanda Havens | Secondary Subway RFP contact; technical/Q&A | Unknown | Rules of Engagement §3; technical evaluation authority unverified.
Suyog Sutar | Additional Subway Procurement contact | Unknown | Rules of Engagement §3.
Stacey (surname to confirm) | Worldpay Subway relationship manager; internal access channel | Internal, not customer buyer | JPR 10:00; relationship status to confirm.
Nicholas Hulayew | Global Payments RFP bid lead in draft Enclosure 5 | Internal | Draft Enclosure 5; JPR 07:39.
Asher Perlmutter | Subway Chief Technology and Commercial Officer | Unknown | Subway leadership roster; not established as RFP buyer.

## Technology Stack
RFP BASELINE AND FIT GATES
Layer | Subway baseline / current evidence | Genius response status | Source / gate
POS | SubwayPOS 8.4.428.50 or higher | KDS integration reported; kiosk integration not currently available. | Enclosure 1 Integration & Environment r15
Payment manager | Subway Payment Manager v9.12.6 or higher | Kiosk response incomplete. | Enclosure 1 Integration & Environment r16
In-store payments | FreedomPay v5.3.8.13 or higher; Ingenico Lane/3600 pairing | Kiosk pairing response incomplete. | Enclosure 1 Integration & Environment r9, r17
Device management | Canopy MDM, Android Enterprise and Splashtop via Canopy | Kiosk/KDS answers incomplete. | Enclosure 1 Integration & Environment r11–13
Custom API | Fresh Connect proprietary APIs; specifications via addendum | KDS integration stated; kiosk response blank. | Enclosure 1 Integration & Environment r25
Store environment | 50/5 Mbps baseline, Meraki-class network, counter/bracket/ADA dimensions | Compatibility and accessibility gaps. | Enclosure 1 Integration & Environment
KDS | Genius reported selection for approx. 2,500 locations | Contracted/live count and outcomes unverified. | Prior internal account brief; verify records

## Commercial Model
STORE-LEVEL ECONOMICS — PRICING PENDING
Item | Current read | Value | Unit / caveat
Program ceiling | Customer planning ceiling, not award quantity | 5000 | U.S. restaurants
Kiosks per store | Customer pricing assumption, not final device count | 3 | kiosks / store
2025 AUV estimate | QSR industry estimate | 490000 | USD / U.S. store / year
Royalty + advertising | 2024 U.S. FDD combined gross-sales charge | 0.125 | 12.5%; before operating costs
Additional $100 monthly fee | Illustrative incremental fee; not a proposed price | 1200 | USD / store / year = 0.245% of estimated AUV
Hardware pricing | Draft grid incomplete |  | Commercial lead approval required
Installation pricing | Draft grid incomplete |  | Site survey/staging/day/after-hours rates needed
DMB pricing | Draft grid incomplete |  | 4-screen wall/ceiling unit rates needed

## Actions
SUBMISSION ACTION AND DECISION REGISTER
Priority | Action / decision | Owner | Closure evidence / target
P0 | Confirm applicable bid scopes and Q&A submission; clarify 25 vs 200 2026 phase through form if window remains open. | Nick / formal event team | Question form receipt; September 15 4 p.m. ET
P0 | Validate kiosk-to-SPOS and Fresh Connect integration path, payment pairing, Canopy, ADA, network and counter fit. | Andy Grindstaff + assigned technical owners | Fully evidenced responses before September 22
P0 | Quantify realistic 2026/2027 installation capacity and partner dependencies. | Services/operations lead to assign | Capacity answer and staffing/OEM model
P0 | Fill hardware, installation and DMB pricing grids and per-store cost bridge. | Michael + authorized commercial lead | Approved native workbooks, 120-day validity
P0 | Complete Enclosure 5 bid roster, signatory, account manager and bid-to-account transition attachment. | Nick / legal Joana Mangum / account owner | Signed and complete Enclosure 5
P1 | Reconcile current Worldpay Subway relationship, meeting context, owner Stacey, lost contact and new-leader outreach, and shared account posture. | Stacey + Nick + account support | Internal relationship map; no off-channel RFP outreach
P0 | Decide current versus next-generation kiosk offering and its validated price, integration and deployment schedule. | Nick + product technical/commercial leads | Approved offer choice and requirement fit before internal draft target
P1 | Build PAR chronology separating 2000–01 hardware loss from later five-to-six-year recollection; check NCR report. | Account intelligence owner | Records and source-qualified competitive read
P1 | Verify Genius KDS selected, signed, installed, live and referenceable counts and outcomes. | Genius KDS owner to assign | Approved records and reference statement
P1 | Rewrite executive summary around actual three scopes and existing SPOS baseline. | Bid lead / marketing | Scoped claims backed by workbooks and price model

## Evidence
SOURCE AND LIMITATION REGISTER
Source | Specific support | Limitations | Date
Subway RFP Enclosures 1–3 and 5 | Scope, terms, contacts, baseline, planned scale and response deadline | 25/200 2026 phase discrepancy; missing MSA, question form and addenda | 2026-09
Draft Global Payments response workbooks | Internal completion tracker, gap flags and proposed responses | Status fields are not technical validation or final sign-off | 2026-09-15
JPR 07:39 call | POS excluded; Nick-led bid; kiosk/pricing decision; lost contact, unanswered technology-leader outreach, NCR and later PAR loss reported | Recording names and terms may be garbled; competitive and chronology claims unverified | 2026-09-15
JPR 10:00 Worldpay call | Stacey named Subway RM; team learned of RFP; prior-day Subway meeting mentioned | Surname, meeting details and relationship health not established | 2026-09-15
Subway 2024 U.S. FDD | Historical U.S. tech and fee requirements | Not proof of 2026 vendor standards | 2024
QSR 50 2026 | U.S. sales and AUV estimate | Estimate; no store-profit inference | 2026
PAR 2014 / 2018 10-Ks | Later PAR Subway relationship after reported 2000–01 loss | Do not infer current RFP incumbency | 2014 / 2018